## Sheet1
Sprint #24 | Status | Comments
US 167846 | Accepted | Completed with open Defect DE57359
US 167845 | Accepted | Completed with open Defect DE57359
US 168023 | Blocked | Pending D&A: Waiting for DE57443 to get resolve
US 168024 | In Progress | DE 57459 to be resolved to progress on testing
US 168027 | In Progress | 19-JUN: Moved to Sprint 25. QA stated US169086 was needed before accomplishing this US.
Sprint #25 | Status | Comments
US168023 | Blocked | Pending D&A: Waiting for DE57443 to get resolve
US168024 | In Progress | DE 57459 to be resolved to progress on testing
US168027 | In Progress | 19-JUN: Moved to Sprint 25. QA stated US169086 was needed before accomplishing this US.
US168030 | Defined | New additions
US168031 | Defined | New additions
US168032 | Defined | New additions